## Project Timeline
Karplus Strong Synthesizer V2 TIMELINE
PROJECT TITLE |  | Karplus Strong Synthesizer V2 |  | COMPANY NAME |  | Bas encorperated
PROJECT MANAGER |  | Bas Maat |  | DATE |  | 2019-05-04
PHASE |  |  | DETAILS
|  |  |  | April |  |  |  | May | [5 empty] | June
| PROJECT WEEK: |  |  | 15 | 22 |  | 29 | 6 |  | 13 |  | 20 | 27 | 3 | 10
1 | Project Conception and Initiation |  | - Concept thinking | Concept thinging | [10 empty] | PROJECT END
|  |  | - Concept construction |  | Concept construction
|  |  | - Creating a planning |  |  |  | Creating a planning
2 | Learn Visual Studio |  | - Understanding the basic Layout |  | Understanding the basic...
|  |  | - Merging with JUICE |  |  |  | Merging with JUICE
3 | Prototyping |  | - Interaction Design |  |  |  |  | Interaction Design
|  |  | - Technical Design |  |  |  |  | Technical Design
4 | Building the application |  | - Main output method |  |  |  |  | Main output method
|  |  | - Delay Line | [5 empty] | Delay Line
|  |  | - Filter | [7 empty] | Filter
|  |  | - Synthesis | [7 empty] | Synthesis
|  |  | - UI | [8 empty] | UI
|  |  | - GUI | [9 empty] | GUI
5 | Documentation |  | - Time Tracking | Time Tracking
-
|  |  | - Concept Updating |  |  |  |  | Concept Updating
6 | Project Close |  | - Testing | [9 empty] | Testing
|  |  | - Finish Reflection and documentation | [9 empty] | Finish Reflection etc.
|  |  | - Buffer | [10 empty] | Buffer